## Sheet1
SPMP Mile Stones | Planned Completion Date | Actual Completion Date | Reason Milestone Was Not Met
Establish Requirements | 2021-02-21 | 2021-02-15
Design Documentation Part 1 | 2021-03-07 | 2021-03-07
Tool Selection | 2021-03-21 | 2021-03-21
Website Creation Part 1 | 2021-04-04 | 2021-03-25
Design Documentation Part 2 | 2021-04-04 | 2021-03-30
Website Creation Part 2 | 2021-04-04 | 2021-04-04
Statistic Tool Creation | 2021-05-03 | N/A
Testing | 2021-05-03 | N/A